## Jan
Month : | JAN
Roll No : | MT2012036 |  | MT2012066 |  | MT2012155
Name : | Vikrantsingh |  | Pridhvi |  | Vaibhav
Date | Activity Code | Hours | Activity Code | Hours | Activity Code | Hours | Activity Code | Activity
2013-01-01 | NA | OFF | NA | OFF | NA | OFF | P01 | Reading past research work.
2013-01-02 | NA | OFF | NA | OFF | NA | OFF | P02 | Understanding the problem statement and requirements.
2013-01-03 | NA | OFF | NA | OFF | NA | OFF | P03 | Analysis of problem statement and existing solutions.
2013-01-04 | NA | OFF | NA | OFF | NA | OFF | P04 | SRS Documentation
2013-01-05 | NA | OFF | NA | OFF | NA | OFF | P05 | Designing of software architecture.
2013-01-06 | NA | OFF | NA | OFF | NA | OFF | P06 | Relevant research and learning about the technologies used in the proposed solution.
2013-01-07 | NA | OFF | NA | OFF | NA | OFF | P07 | Coding and Unit Testing.
2013-01-08 | NA | OFF | NA | OFF | NA | OFF | P08 | Documentation for user manuals and guides
2013-01-09 | NA | OFF | NA | OFF | NA | OFF | P09 | System Testing.
2013-01-10 | NA | OFF | NA | OFF | NA | OFF | P10 | Review.
2013-01-11 | NA | OFF | NA | OFF | NA | OFF | P11 | Bug Fixing and Re-testing.
2013-01-12 | NA | OFF | NA | OFF | NA | OFF
2013-01-13 | NA | OFF | NA | OFF | NA | OFF
2013-01-14 | NA | OFF | NA | OFF | NA | OFF
2013-01-15 | NA | OFF | NA | OFF | NA | OFF
2013-01-16 | NA | OFF | NA | OFF | NA | OFF
2013-01-17 | NA | OFF | NA | OFF | NA | OFF
2013-01-18 | NA | OFF | NA | OFF | NA | OFF
2013-01-19 | NA | OFF | NA | OFF | NA | OFF
2013-01-20 | NA | OFF | NA | OFF | NA | OFF
2013-01-21 | NA | OFF | NA | OFF | NA | OFF
2013-01-22 | NA | OFF | NA | OFF | NA | OFF
2013-01-23 | NA | OFF | NA | OFF | NA | OFF
2013-01-24 | NA | OFF | NA | OFF | NA | OFF
2013-01-25 | P01 | 1 | P01 | 1 | P01 | 1
2013-01-26 | P01 | 1 | P01 | 1 | P01 | 1
2013-01-27 | P01 | 1 | P01 | 1 | P01 | 1
2013-01-28 | P01 | 1 | P01 | 1 | P01 | 1
2013-01-29 | NA | OFF | NA | OFF | NA | OFF
2013-01-30 | NA | OFF | NA | OFF | NA | OFF
2013-01-31 | NA | OFF | NA | OFF | NA | OFF

## Feb
Month : | FEB
Roll No : | MT2012036 |  | MT2012066 |  | MT2012155
Name : | Vikrantsingh |  | Pridhvi |  | Vaibhav
Date | Activity Code | Hours | Activity Code | Hours | Activity Code | Hours | Activity Code | Activity
2013-02-01 | P01 | 1 | P01 | 1 | P01 | 1 | P01 | Reading past research work.
2013-02-02 | P02 | 1 | P02 | 1 | P02 | 1 | P02 | Understanding the problem statement and requirements.
2013-02-03 | P02 | 1 | P02 | 1 | P02 | 1 | P03 | Analysis of problem statement and existing solutions.
2013-02-04 | P03 | 0.5 | P03 | 0.5 | P03 | 0.5 | P04 | SRS Documentation
2013-02-05 | NA | OFF | NA | OFF | NA | OFF | P05 | Designing of software architecture.
2013-02-06 | P03 | 1 | P03 | 1 | P03 | 1 | P06 | Relevant research and learning about the technologies used in the proposed solution.
2013-02-07 | NA | OFF | NA | OFF | NA | OFF | P07 | Coding and Unit Testing.
2013-02-08 | NA | OFF | NA | OFF | NA | OFF | P08 | Documentation for user manuals and guides
2013-02-09 | P03 | 1 | P03 | 1 | P03 | 1 | P09 | System Testing.
2013-02-10 | NA | OFF | NA | OFF | NA | OFF | P10 | Review.
2013-02-11 | NA | OFF | NA | OFF | NA | OFF | P11 | Bug Fixing and Re-testing.
2013-02-12 | NA | OFF | NA | OFF | NA | OFF
2013-02-13 | P04 | 1 | P04 | 1 | P04 | 1
2013-02-14 | NA | OFF | NA | OFF | NA | OFF
2013-02-15 | NA | OFF | NA | OFF | NA | OFF
2013-02-16
2013-02-17
2013-02-18
2013-02-19
2013-02-20
2013-02-21
2013-02-22
2013-02-23
2013-02-24
2013-02-25
2013-02-26
2013-02-27
2013-02-28

## Mar
Month : | Mar
Roll No : | MT2012036 |  | MT2012066 |  | MT2012155
Name : | Vikrantsingh |  | Pridhvi |  | Vaibhav
Date | Activity Code | Hours | Activity Code | Hours | Activity Code | Hours | Activity Code | Activity
2013-03-01 | P07 | 2 | P07 | OFF | P07 | 1 | P01 | Reading past research work.
2013-03-02 | P07 | OFF | P07 | 2 | P07 | OFF | P02 | Understanding the problem statement and requirements.
2013-03-03 | P07 | OFF | P07 | OFF | P07 | OFF | P03 | Analysis of problem statement and existing solutions.
2013-03-04 | P07 | 1 | P07 | 1 | P07 | 2 | P04 | SRS Documentation
2013-03-05 | P07 | 1 | P07 | 1 | P07 | 1 | P05 | Designing of software architecture.
2013-03-06 | P07 | OFF | P07 | OFF | P07 | OFF | P06 | Relevant research and learning about the technologies used in the proposed solution.
2013-03-07 | P07 | 2 | P07 | 2 | P07 | OFF | P07 | Coding and Unit Testing.
2013-03-08 | P07 | 1 | P07 | OFF | P07 | 2 | P08 | Documentation for user manuals and guides
2013-03-09 | P07 | OFF | P07 | 1 | P07 | 1 | P09 | System Testing.
2013-03-10 | P07 | OFF | P07 | OFF | P07 | OFF | P10 | Review.
2013-03-11 | P07 | 1 | P07 | 1 | P07 | 1 | P11 | Bug Fixing and Re-testing.
2013-03-12 | P07 | OFF | P07 | OFF | P07 | 1
2013-03-13 | P07 | 2 | P07 | OFF | P07 | OFF
2013-03-14 | P07 | 1 | P07 | 3 | P07 | 1
2013-03-15 | P07 | 2 | P07 | OFF | P07 | 1
2013-03-16 | P07 | 1 | P07 | 1 | P08 | 1
2013-03-17 | P07 | 2 | P07 | OFF | P08 | 2
2013-03-18 | P07 | 1 | P07 | 2 | P07 | 1
2013-03-19 | P07 | 1 | P07 | 3 | P07 | 2
2013-03-20 | P07 | 3 | P07 | 1 | P07 | OFF
2013-03-21 | P07 | 1 | P07 | 2 | P07 | 2
2013-03-22 | P07 | 2 | P07 | 2 | P07 | 1
2013-03-23 | P07 | 1 | P07 | 1 | P07 | 1
2013-03-24 | P07 | 2 | P07 | 3 | P07 | 3
2013-03-25 | P07 | 1 | P07 | 2 | P07 | 1
2013-03-26 | P07 | 2 | P07 | 1 | P07 | 1

## Apr
Month : | Apr
Roll No : | MT2012036 |  | MT2012066 |  | MT2012155
Name : | Vikrantsingh |  | Pridhvi |  | Vaibhav
Date | Activity Code | Hours | Activity Code | Hours | Activity Code | Hours | Activity Code | Activity
2013-04-01 | P07 | 1 | P07 | 1 | P07 | 1 | P01 | Reading past research work.
2013-04-02 | P09 | 1 | P07 | 1 | P07 | 1 | P02 | Understanding the problem statement and requirements.
2013-04-03 | P07 | 2 | P07 | 1 | P07 | 1 | P03 | Analysis of problem statement and existing solutions.
2013-04-04 | P08 | 4 | P08 | 4 | P08 | 4 | P04 | SRS Documentation
2013-04-05 | P08 | 4 | P08 | 4 | P08 | 4 | P05 | Designing of software architecture.
2013-04-06 | P07 | OFF | P07 | OFF | P07 | OFF | P06 | Relevant research and learning about the technologies used in the proposed solution.
2013-04-07 | P07 | OFF | P07 | OFF | P07 | OFF | P07 | Coding and Unit Testing.
2013-04-08 | P09 | OFF | P09 | OFF | P09 | OFF | P08 | Documentation for user manuals and guides
2013-04-09 | [6 empty] | P09 | System Testing.
2013-04-10 | [6 empty] | P10 | Review.
2013-04-11 | [6 empty] | P11 | Bug Fixing and Re-testing.
2013-04-12
2013-04-13
2013-04-14
2013-04-15
2013-04-16
2013-04-17
2013-04-18
2013-04-19
2013-04-20
2013-04-21
2013-04-22
2013-04-23
2013-04-24
2013-04-25
2013-04-26
2013-04-27
2013-04-28
2013-04-29
2013-04-30